## Risk Register
Risk ID | Risk Description | Risk Category | Asset | Threat | Vulnerability | Likelihood | Impact | Risk Score | Risk Owner | Existing Controls | Treatment Plan | Target Risk Level | Review Date | Status | Comments
R001 | Phishing Attack | Cyber | Employee Email | Hacker | Lack of awareness | 4 | 5 | 20 | IT Manager | Basic Antivirus | Awareness Training + MFA | Medium | 31-Dec-2026 | Open | High priority training focus
R002 | Ransomware | Cyber | File Server | Malware | Unpatched systems | 4 | 5 | 20 | IT Manager | Daily local backups | Patch Management & Offline Backups | Medium | 31-Dec-2026 | Open | Critical infrastructure risk
R003 | Weak Passwords | Cyber | User Accounts | Unauthorized Access | Weak password policy | 4 | 4 | 16 | IT Manager | Minimum 8 chars | Strong password policy + MFA | Low | 31-Dec-2026 | Open | Enforcement scheduled next month
R004 | Data Leakage | Compliance | Customer Database | Insider | Excessive permissions | 3 | 5 | 15 | GRC Analyst | Standard db access controls | Access Reviews & Data Masking | Low | 31-Dec-2026 | Open | NDAs signed by all staff
R005 | Insider Threat | Operational | Company Files | Employee | Lack of monitoring | 3 | 4 | 12 | HR Manager | Basic file logging | Monitoring & Awareness | Medium | 31-Dec-2026 | Open | Coordinated with security team
R006 | Lost Laptop | Physical | Company Laptop | Theft | No encryption | 3 | 4 | 12 | IT Manager | BIOS Passwords | Full Disk Encryption | Low | 31-Dec-2026 | Open | MDM rollout in progress
R007 | Cloud Misconfiguration | Cyber | Cloud Storage | Human Error | Incorrect settings | 3 | 5 | 15 | Cloud Admin | Default cloud policies | Configuration Reviews | Low | 31-Dec-2026 | Open | Automated alerts being set up
R008 | Vendor Failure | Operational | Third-party Service | Supplier | No backup vendor | 2 | 4 | 8 | Procurement Manager | SLA Agreements | Vendor Assessment & SLA Revision | Low | 31-Dec-2026 | Open | Reviewing secondary vendors
R009 | Unpatched Systems | Cyber | Servers | Cyber Attack | Missing updates | 4 | 5 | 20 | IT Manager | Manual patches | Monthly Patching Policy | Medium | 31-Dec-2026 | Open | Vulnerability scanning scheduled
R010 | Power Outage | Physical | Office Infrastructure | Utility Failure | No UPS | 2 | 3 | 6 | Operations Manager | Surge protectors | Install UPS & Generator contract | Low | 31-Dec-2026 | Open | Facilities managing vendor bids
R-011 | DDoS Attack | Cyber | Public Website | Hacker | Bandwidth saturation | 3 | 4 | 12 | IT Manager | Basic firewall | Cloud DDoS Protection Integration | Low | 31-Dec-2026 | Open | Evaluating CDN providers
R-012 | Employee Data Privacy Violation | Compliance | HR System | Regulatory Penalty | Improper processing | 3 | 5 | 15 | HR Manager | Basic access controls | Privacy Training & Policy Alignment | Low | 31-Dec-2026 | Open | Aligning with local UAE laws
R-013 | Unauthorized Physical Access | Physical | Server Room | Intruder | No keycard logging | 2 | 5 | 10 | Operations Manager | Standard key lock | Biometric access & CCTV installation | Low | 31-Dec-2026 | Open | Physical perimeter audit complete
R-014 | Backup Failure | Operational | Backup Storage | System Fault | No verification drills | 3 | 4 | 12 | IT Manager | Automated email alerts | Weekly backup restoration testing | Low | 31-Dec-2026 | Open | Test schedule created
R-015 | Social Engineering Attack | Cyber | Helpdesk Systems | Vishing/Impersonation | No caller verification | 4 | 3 | 12 | IT Manager | None | Helpdesk verification protocols & training | Low | 31-Dec-2026 | Open | Procedures being updated